## Sheet
SNO. | ABN.ID | ABN.TYPE | SUBHEAD | REPORTSTTN | FROM | TO | CREW/CLIID | CREW/CLINAME | DESIG | ABNDATE | ABN.TIME | FROMKM | TO KM | STATUS | FILLEDBY | LOCO | TRAIN | SMSTO LP | FrwdByLoc | FrwdByUser | FrwdDateTime | FrwdByAuth | Div | RemStts | Detail | Closing Remarks | Forwarding Remarks | App Remarks | Reporting Date
1 | KGP/11-10-2024/ENGG/1 | ENGG | ENGG BOARDS | KGP | NYA | VKD | KGP0025 | EL H. MURMU | Chief Loco Inspector | 11-10-2024 | 08:20 | 140/23X | 140/25X | YS | APPUSER | 43336 | MLPM AUTO | 11-10-24 20:18 |  |  |  |  | KGP | Y | DETAIL:UP joint line between NYA-VKD, Caution Indicator at Km 140/25X and Speed indicator at Km141/17X. The caution indicator may be in about 720 M. | CLOSE_REM:REMARK GIVEN BY ENGG DEPT. |  | APP_REM:@ENGKGP/11-10-2024 15:10-Placed At Proper Location. | 11-10-2024 08:51
2 | KGP/11-10-2024/ENGG/2 | ENGG | ENGG BOARDS | KGP | BLDA | BLDA | KGP0025 | EL H. MURMU | Chief Loco Inspector | 11-10-2024 | 08:38 | 152/1 | 152/1 | YS | APPUSER | 43336 | MLPM AUTO | 11-10-24 20:18 |  |  |  |  | KGP | Y | DETAIL:BLDA UP yard found an old cross over cleared board at KM 152/1, may be corrected. | CLOSE_REM:REMARK GIVEN BY ENGG DEPT. |  | APP_REM:@ENGKGP/11-10-2024 15:11-Complied | 11-10-2024 09:00
3 | KUR/11-10-2024/ENGG/3 | ENGG | OTHER | BBS | LXD | DNT | KUR0022 | Sri SUSANTA KU MOHAPATRA | Chief Loco Inspector | 11-10-2024 | 14:56 |  |  | YS | APPUSER | 39197 | 12704 | 11-10-24 20:18 |  |  |  |  | KGP | Y | DETAIL:Between LXD-DNT, Tree Branches From 175/20-18 Obstructed LC-41 GATE Home Signal . | CLOSE_REM:REMARK GIVEN BY ENGG DEPT. |  | APP_REM:@ENGKGP/11-10-2024 15:10-Will Be Complied On 12.10.24. | 11-10-2024 14:58